## Sheet1
| Early Move | 2008-01-02 | 2008-01-03 | 2008-01-04 | 2008-01-07 | 2008-01-08 | 2008-01-09 | 2008-01-10 | 2008-01-11 | 2008-01-14 | 2008-01-15 | 2008-01-16 | 2008-01-17 | 2008-01-18
Mathematics and Statistics |  | 2008-01-02: 4 students (all day), 2 movers (pm); 2008-01-03: 4 students (all day), 2 movers (pm); 2008-01-04: 2 students (all day), 2 movers (pm); 2008-01-11: 2 students (pm)
Dept-based Students:
Other Students: |  | 2008-01-02: 4; 2008-01-03: 4; 2008-01-04: 2; 2008-01-11: 1
Movers: | bar: 2008-01-02 to 2008-01-04
|  | AM: Pack: Shonda Kuiper in Room 2612 | AM: Pack: Emily Moore in 2611
|  | AM: Pack: David Romano in 3814 | AM: Pack: Tom Moore in 2610
AM: Pack: Marc Chamberland in 2609
|  | PM: Move: David Romano from 3814 to 2519 | PM: Move: Emily Moore from 2611 to 2516 | PM: Move: Chris French from 2608 to 2041
|  | PM: Move: Royce Wolf from 2002 to 2521 | PM: Move: Tom Moore from 2610 to 2515 | PM: Move: Karen Shuman from 2220 to 2249
PM: Move: Holly Mosley from 2216 to 2514
PM: Move: Shonda Kuiper from 2612 to 2042
PM: Move: Marc Chamberland from 2609 to 2522
|  | PM: Unpack: Shonda Kuiper in Room 2042 | PM: Unpack: Emily Moore in Room 2516 | [5 empty] | PM: Unpack: Marc Chamberland in Room 2522
|  | PM: Unpack: David Romano in Room 2519 | PM: Unpack: Tom Moore in Room 2515
Psychology
Dept-based Students
Other Students: |  | 2008-01-08: 4; 2008-01-09: 2; 2008-01-10: 2; 2008-01-11: 2
Movers: |  | 2008-01-08: 4; 2008-01-09: 2; 2008-01-10: 1; 2008-01-14: 2
[6 empty] | AM 8-10: Move Sinnett: Move furniture from 0421 to 1519/1520/1523, 3 of 4 (tall) oak bookshelves from 0411 to 1523, 2 metal utility cabinets from 0411 to 1523, 1 (short, lon) oak bookshelv from 0411 to 1519. Move boxes from 0421 to 1519/1520 and another | AM 8-10: Move Gibson from 0423 and 3828 to 1524 | AM 8-10: Move/unpack boxes from Psych Commons to 1514 | All Day: Help unpack, set up 0421/0422/0423
[6 empty] | AM 10-11: Pack cabinet contents in 1513 | AM 10-noon: Pack/move/unpack computers, tables, boxes from 1514 to 1517/1516
AM 11-noon: Move boxes from 1514 to Psych Commons (temporarily).
[5 empty] | Some new furniture arrives and is placed in rooms | Furniture from trailers to 1524 (Gibson), 1516/1517 (Brown), 1523 (storage) | Sofa and recliner from trailers to 1522 (Drwal)
[5 empty] | Move furniture as room finishes in 1986 wing allow | Move furniture: file cabinets from 1514 to 1517 (Brown), furniture from 0421 to 1519/1520/1523 (Sinnett), desk and tables from 1303 to 1526-1529 (Jaworski), computer cart from 1303 to 1608, metal cabinet & tool chest & short Lista cabinet from 1513 to 15 |  |  |  | Lopatto furniture to various locations, 2 metal cabinets from 1513 to 0505, 1 metal cabinet from 1513 to 0511
[6 empty] | Assemble workbench in 1524, workbench in 1517/1516, |  | Assemble workbench in 0421-0423 |  | Adjust table height: 1515 (new furniture)
Install wall-mounted cabinets from storage in 1524 (Gibson), 1529(Lopatto)
[6 empty] | PM 1-3: unpack Sinnett: boxes to cabinet in 1523 | PM 1-3: unpack Sinnett: boxes to cabinet in 1523 | PM 1-4: Move/Unpack Drwal: Boxes, computers, small furniture from 1620 to 1522/1247
PM 3-4: Move Lopatto: Move boxes & furniture from 0422 to 1529 (furn will need to be rearranged 1/10)
Physics: | [6 empty] | 3 students (all day) | 3 students (all day) | 3 students (all day) | 3 students (all day), 2 movers (pm) | 3 students (all day), 2 movers (pm) | 3 students (all day), 2 movers (pm) | 3 students (all day), 2 movers (pm) | 3 students (all day), 2 movers (pm)
Dept-based Students | bar: 2008-01-09 to 2008-01-18
Other Students: | [6 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Movers: |  | 2008-01-10: Move intro equipment out of electronics lab 0034 (put intro equipment in hallway); move tables from storage to 0034; 2008-01-14: 1; 2008-01-15: 1; 2008-01-16: 1; 2008-01-17: 1; 2008-01-18: 1
[7 empty] | Move intro equipment out of electronics lab 0034 (put intro equipment in hallway); move tables from storage to 0034 |  | finish set up of 0034 | set up shelving in 0507; move equipment to 0507; move furniture to 0506, 0507, 0508 from 1951 wing hallway and from storage; | set up shelving in 0507; move equipment to 0507; move furniture to 0506, 0507, 0508 from 1951 wing hallway and from storage; | set up shelving in 0507; move equipment to 0507; move furniture to 0506, 0507, 0508 from 1951 wing hallway and from storage; | set up shelving in 0507; move equipment to 0507; move furniture to 0506, 0507, 0508 from 1951 wing hallway and from storage; | set up shelving in 0507; move equipment to 0507; move furniture to 0506, 0507, 0508 from 1951 wing hallway and from storage;
Dept-based Students |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Other Students Needed |  | 4 | 4 | 2 | 4 | 2 | 4 | 4 | 5 | 2 | 2 | 2 | 2 | 2
Total Movers Needed |  | 1 | 1 | 1 | 4 | 2 | 1 | #VALUE! | 0 | 3 | 1 | 1 | 1 | 1